## Plan
Max Hours: | 120 | (between 150 and 120 depending on how many hours we change for budget)
|  |  | Week | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15
Task Name | Duration | Complete | Commencing Monday | 2016-04-04 | 2016-04-11 | 2016-04-18 | 2016-04-25 | 2016-05-02 | 2016-05-09 | 2016-05-16 | 2016-05-23 | 2016-05-30 | 2016-06-06 | 2016-06-13 | 2016-06-20 | 2016-06-27 | 2016-07-04 | 2016-07-11
Submit Team | 0 | Yes |  | 2016-04-04: 2016-04-08
Initial Team Meeting | 0 | Yes |  | 2016-04-11: 2016-04-13
Product Research | 5 | No |  | 2016-04-18: 2016-04-20
Select Hardware | 2 | No | bar: 2016-04-18 to 2016-04-25
Hardware Ordered | 2 | No |  | 2016-04-25: 2016-05-01
Build Hardware | 5 | No | bar: 2016-04-25 to 2016-05-02
Sort Driver Issues | 2 | No | bar: 2016-05-02 to 2016-05-09
Build Dev Environment | 5 | No |  | 2016-05-09: 2016-05-11
Development | 60 | No |  | 2016-06-27: 2016-06-30
Plan Test Environment | 2 | No | bar: 2016-05-23 to 2016-06-06
Dev Mid-Point Review | 1 | No |  | 2016-05-30: 2016-06-02
Testing | 15 | No | bar: 2016-06-06 to 2016-07-04
Final Deployment | 2 | No |  | 2016-07-11: 2016-07-12
Portfolio development | 10 | No | bar: 2016-04-25 to 2016-07-11
Blog posts | 1 | No | bar: 2016-04-11 to 2016-07-04
Create Presentation Materials | 5 | No |  | 2016-07-11: 2016-07-13
Judging Day | 0 | No |  | 2016-07-11: 2016-07-15
Total Hours | 117
Buffer Hours | 3
Team |  |  |  | 2016-05-02: Booking Numbers
Kodiak Jack and the Red Trouser Gang 2
Key
Team Members |  |  |  | 2016-04-04: 00/00/2016; 2016-04-11: Challenge Deadline
Alex Bowyer |  |  |  | 2016-04-11: Work
Stuart Dagnall |  |  |  | 2016-04-04: 00/00/2016; 2016-04-11: Internal Deadline
Chris Eastwood
Chris Mcilree
Andrew Smith
Simon Toms

## Hours
| Week | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15
| Commencing Monday | 2016-04-04 | 2016-04-11 | 2016-04-18 | 2016-04-25 | 2016-05-02 | 2016-05-09 | 2016-05-16 | 2016-05-23 | 2016-05-30 | 2016-06-06 | 2016-06-13 | 2016-06-20 | 2016-06-27 | 2016-07-04 | 2016-07-11 | Totals
Alex Bowyer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stuart Dagnall |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chris Eastwood |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chris Mcilree |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Andrew Smith |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Simon Toms |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2016-07-04: Total booked by all: | 0